## Sheet1
Task	30/01/12	06/02/12	13/02/12	20/02/12	27/02/12	05/03/12	12/03/12	19/03/12	26/03/12	02/04/12	09/04/12	16/04/12	23/04/12	30/04/12	07/05/12
Project Plan		28hr	36% Complete
Gantt Char and Work Breakdown (es, ke)		6hr	0% Complete
Risk Analysis (om)		2hr	0% Complete
Time Budgeting (kc)		2hr	0% Complete
Version Management (by)		3hr	0% Complete
Meetings (es, ke, om, kc, by)	10hr	100% Complete
Reviewing (es, ke, om, kc, by)		5h	0% Complete

Analysis & Design & Testing								63hr							0% Complete
Title page, introductions, revision history		3hr	0% Complete
Use Case Diagrams			2hr			0% Complete
Description of Approach			3hr			0% Complete
Class and Sequence Diagrams			5hr			0% Complete
Wireframes and UI flow Diagrams			5hrs			0% Complete
Test Plan				5hr		0% Complete
Partial Test Report														10hr	0% Complete
Meetings (es, ke, om, kc, by)									25hr						0% Complete
Reviewing (es, ke, om, kc, by)														5hr	0% Complete

Programming									180hr						0% Complete
Model								40hr				0% Complete
View								60hr				0% Complete
Controller								40hr				0% Complete
Integration												40hr			0% Complete

Presentation														30hr
Discuss and group preparation														20hr		0% Complete
Prepare Slides														5hr	0% Complete
Rehearsal															5hr	0% Complete

Final Report													50hr		0% Complete