## Sheet1
|  | Edward | Kristian | Brian | Oscar | Kelvin |  | Edward | Kristian | Brian | Oscar | Kelvin |  | Edward | Kristian | Brian | Oscar | Kelvin
| Week 1 : 19.5 hours | 5 | 5 | 3.5 | 3 | 3 | Week 1 | 5 | 5 | 3.5 | 3 | 3 | Project Plan | 5 | 5 | 3.5 | 3 | 3
1 | Project Plan : 19.5 hours | [5 empty] | Week 2 | 1 | 1.5 | 1 | 2 | 1 | ADT | 16 | 4.5 | 8 | 6 | 3.25
2 | Gantt Chart and Work Breakdown | 4 | 4 |  |  |  | Week 3 | 7 | 3 | 2 | 8.75 | 5.25 | Programming | 17.75 | 17 | 15 | 15 | 11
3 | Risk Analysis |  |  |  | 2 |  | Week 4 | 1 | 7 | 1.5 | 2.5 | 3.5 | Testing |  |  |  |  | 2.5
4 | Budget |  |  |  |  | 2 | Week 5 | 11 | 7 | 6 | 7.75 | 7.25 | First Presentation | 6 | 6 | 6 | 6 | 7
5 | Project Management |  |  | 2.5 |  |  | Week 6 | 0 | 0 | 6 | 0 | 0 | Final Report |  |  | 1 | 2.5 | 10
6 | Reviewing | 1 | 1 | 1 | 1 | 1 | Week 7 | 0 | 0 | 6 | 3.5 | 0
| Week 2 : 6.5 hours | 1 | 1.5 | 1 | 2 | 1 | Week 8 | 12.25 | 0 | 2 | 5 | 8
7 | Analysis, Design and Testing : 6.5 hours | [5 empty] | Week 9 | 9.5 | 9 | 5.5 | 0 | 10
8 | Title, Introduction and Revision History | 1
9 | Description of Approach |  | 1.5
10 | UML for Requirements |  |  | 1 |  | 1
12 | Human Computer Interaction |  |  |  | 2
| Week 3 : 26 hours | 7 | 3 | 2 | 8.75 | 5.25
7 | Analysis, Design and Testing : 16.25 hours
8 | Title, Introduction and Revision History |  |  |  |  | 0.25
9 | Description of Approach |  | 1
11 | UML for Design | 1
12 | Human Computer Interaction | 2 |  |  | 2
15 | Reviewing | 2 | 2 | 2 | 2 | 2
16 | Programming : 9.75 hours
17 | Model |  |  |  | 4.75 | 3
18 | View | 2
| Week 4 : 15.5 hours | 1 | 7 | 1.5 | 2.5 | 3.5
7 | Analysis, Design and Testing : 2.5 hours
12 | Human Computer Interaction | 1
13 | Test plan |  |  | 1.5
16 | Programming : 13 hours
17 | Model |  |  |  | 2.5 | 3.5
18 | View |  | 7
| Subtotal | 14 | 16.5 | 8 | 16.25 | 12.75
| Process / Member | Edward | Kristian | Brian | Oscar | Kelvin
| Week 5 : 38 hours | 11 | 7 | 6 | 7.75 | 7.25
7 | Analysis, Design and Testing : 2.5 hours
12 | Human Computer Interaction | 2.5
16 | Programming : 5.5 hours
17 | Model |  |  |  | 1.75 | 0.5
18 | View | 2.5 | 1
24 | Presentation : 30 hours
25 | Discussion and Group Preparation | 4 | 4 | 4 | 4 | 4
26 | Prepare Slides | 1 | 1 | 1 | 1 | 2
27 | Rehearsal | 1 | 1 | 1 | 1 | 1
| Week 6 : 6 hours | 0 | 0 | 6 | 0 | 0
16 | Programming : 6 hours
18 | View |  |  | 2
19 | Controller |  |  | 4
| Week 7 : 9.5 hours | 0 | 0 | 6 | 3.5 | 0
16 | Programming : 9.5 hours
17 | Model |  |  |  | 3.5
19 | Controller |  |  | 6
| Week 8 : 27.25 | 12.25 | 0 | 2 | 5 | 8
7 | Analysis, Design and Testing : 4 hours
9 | Description of Approach | 1.5
2012-11-10 | UML | 0.5
13 | Test plan | 1 |  | 2
16 | Programming : 15.75 hours
17 | Model | 0.5 |  |  | 2.5 | 4
18 | View | 2
19 | Controller | 2.5
20 | Integration | 4.25
21 | Testing : 2.5 hours
22 | Unit testing |  |  |  |  | 2.5
32 | Final Report : 6.5 hours
32 | Final Report |  |  |  | 2.5 | 4
| Week 9 : | 9.5 | 9 | 5.5 | 0 | 3
7 | Analysis, Design and Testing
9 | Description of Approach | 1.5
10 | UML for Requirements | 1
11 | UML for Design | 2
12 | Human Computer Interaction | 1 |  | 1.5
13 | Reviewing
16 | Programming
18 | View | 2 | 9
19 | Controller | 2 |  | 3
32 | Final Report
32 | Final Report |  |  | 1 |  | 6.5
| Subtotal | 46.75 | 31.5 | 27 | 32.5 | 37
| Formal & informal meetings | 14 | 14 | 14 | 14 | 14
Total
Breakdown
1 | Project Plan : 19.5 h | 5 | 5 | 3.5 | 3 | 3
7 | Analysis, Design & Testing : 38.75 h | 16 | 4.5 | 8 | 6 | 3.25
16 | Programming : 75.5 h | 17.75 | 17 | 15 | 15 | 11
21 | Testing : 2.5 h |  |  |  |  | 2.5
24 | First Presentation : 30 h | 6 | 6 | 6 | 6 | 6
32 | Final Report : 10.5 h |  |  | 1 | 2.5 | 10